## Setup
Store Launch Marketing Checklist
Control the full launch window from pre-opening buzz through the first 30 days of trading.
Document control
Audience | Expansion teams, founders, area managers, brand and marketing leads
Primary outcome | A launch sequence that covers digital, local, in-store, and CRM work instead of collapsing into one weekend event.
Version | 1.0
Last updated | 19-Apr-2026
Editable cells | Amber cells
Review rhythm | Weekly during active campaigns, monthly for planning
What this workbook helps you control
1. Separate pre-launch, opening-week, and first-30-day tasks so momentum does not end after day one.
2. Keep local outreach, Google readiness, and content production visible alongside launch offers.
3. Use the dashboard to spot which launch phase is slipping before the store goes live.
Input cell | Starter assumption or editable user entry
Formula cell | Calculated output - keep these logic cells intact
Control note | Use this area for assumptions, approvals, and reviewer sign-off
Tab | Purpose
Checklist | The master launch tracker across phases, owners, and deadlines.
Launch_Calendar | A week-by-week rhythm for the soft opening, launch burst, and first 30 days.
Dashboard | Completion status by phase so launch readiness is easy to review.

## Checklist
Launch Checklist
Use one row per launch task. Add as many operational or local tasks as needed.
How to use this tab
1. Keep this shared with operators so marketing launch work stays grounded in actual opening reality.
Phase | Task | Channel or area | Owner | Due date | Status | Priority | Budget | Notes
Pre-launch | Claim and verify Google Business Profile | Google / local SEO | SEO lead | 2026-04-10 | In progress | High | 0 | Set ordering and menu links before launch.
Pre-launch | Build launch landing page and lead capture | Website / CRM | Growth lead | 2026-04-12 | Approved | High | 0 | Collect VIP waitlist before opening week.
Pre-launch | Finalize launch content shoot | Content | Content lead | 2026-04-15 | Ready | High | 4500 | Need storefront, hero items, and team shots.
Soft opening | Friends and family service | Store experience | GM | 2026-04-18 | Not started | High | 3500 | Use feedback form and test full menu flow.
Soft opening | Micro-influencer seeding | Social / PR | Brand lead | 2026-04-19 | Approved | Medium | 2500 | Invite only locally relevant creators.
Launch week | Grand opening offer live | In-store + Meta | Growth lead | 2026-04-22 | Not started | High | 7000 | Keep offer margin-aware and time-limited.
Launch week | Local flyer and partner drop | Trade area | Store lead | 2026-04-22 | In progress | Medium | 1800 | Focus offices, gyms, and residential buildings.
Launch week | Launch-day stories and UGC reposts | Social | Social exec | 2026-04-22 | Ready | High | 0 | Prepare story templates before day one.
First 30 days | Welcome-back CRM sequence | Email / WhatsApp | CRM lead | 2026-04-27 | Not started | High | 1200 | Target launch-week guests with second-visit offer.
First 30 days | Review generation push | Google / reputation | Store lead | 2026-04-29 | Ready | Medium | 0 | Train team to ask at peak satisfaction moments.
First 30 days | First menu performance review | Menu / analytics | GM | 2026-05-05 | Not started | High | 0 | Check hero items, attach rates, and waste.
First 30 days | Local office partnership test | Trade area | Partnership lead | 2026-05-07 | Not started | Medium | 1500 | Lunch vouchers and meeting platters.

## Launch_Calendar
Launch Rhythm
A simple week-by-week plan to keep the launch moving after the opening event.
Week | Focus | Primary message | Hero channel | KPI | Owner
W-2 | Awareness build | We open soon - join the local list | Meta + landing page | Lead capture | Growth lead
W-1 | Soft opening proof | See the store, team, and first reactions | Stories + creators | Content saves | Content lead
Launch week | Grand opening urgency | Come in now while the opening offer is live | Meta + in-store | Transactions | GM
Week 2 | Return visit | Back for the second trip, not just the first one | CRM | Repeat visits | CRM lead
Week 3 | Local partnerships | We are part of this neighborhood | Trade area | Partner traffic | Store lead
Week 4 | Habit formation | Build the weekday or weekend ritual | Meta + CRM | Frequency | Growth lead

## Dashboard
Launch Dashboard
Review completion by phase before the store or campaign goes live.
Launch readiness | Value
Total tasks | 10
Completed tasks | 0
Blocked tasks | 0
Launch budget | 20500
Phase | Completed / live tasks
Pre-launch | 0
Soft opening | 0
Launch week | 0
First 30 days | 0