## Setup
Franchise Campaign Rollout Tracker
Track centralized campaign rollout without losing visibility into local readiness and compliance.
Document control
Audience | Franchise marketing teams, multi-unit operators, area managers, brand governance leads
Primary outcome | A cleaner store-by-store rollout view with compliance and launch status in the same file.
Version | 1.0
Last updated | 19-Apr-2026
Editable cells | Amber cells
Review rhythm | Weekly during active campaigns, monthly for planning
What this workbook helps you control
1. Keep central asset distribution and local adaptation approvals visible together.
2. Track store compliance as a management signal, not an afterthought.
3. Use region-based dashboard views to see where rollout friction is clustering.
Input cell | Starter assumption or editable user entry
Formula cell | Calculated output - keep these logic cells intact
Control note | Use this area for assumptions, approvals, and reviewer sign-off
Tab | Purpose
Stores | The store roster and compliance snapshot.
Campaign_Rollout | Campaign-by-store rollout tracking.
Dashboard | Average compliance and readiness by region.

## Stores
Store Roster
Track branch format, stage, and compliance in one place.
Store | City | Region | Format | Launch stage | Local lead | Compliance % | Go-live date | Status
Jumeirah Beach Road | Dubai | Dubai | Cafe | Operating | Sara | 92% | 2025-09-10 | Live
Marina Promenade | Dubai | Dubai | Cafe | Operating | Faisal | 87% | 2025-11-02 | Live
Yas Bay | Abu Dhabi | Abu Dhabi | Fast casual | Opening soon | Omar | 74% | 2026-05-12 | Ready
Aljada | Sharjah | Sharjah | QSR | Pipeline | Maha | 58% | 2026-08-20 | In progress
West Bay | Doha | Doha | Cafe | Operating | Lina | 81% | 2025-12-01 | Live
Olaya | Riyadh | Riyadh | Cloud kitchen | Opening soon | Hassan | 69% | 2026-06-18 | Approved

## Campaign_Rollout
Campaign Rollout
Use one row per campaign and store pairing when local rollout matters.
Store | Campaign | Asset pack sent | Local adaptation approved | Media live | Post-launch review | Status | Notes
Jumeirah Beach Road | Summer cold drinks | Yes | Yes | Yes | Yes | Complete | Strong compliance and fast go-live.
Marina Promenade | Summer cold drinks | Yes | Yes | Yes | No | Live | Waiting on week-one review.
Yas Bay | Opening launch burst | Yes | No | No | No | Ready | Local mall media version not approved yet.
Aljada | Breakfast combo reset | No | No | No | No | Not started | Store still in pipeline stage.
West Bay | Corporate catering push | Yes | Yes | Yes | No | Live | Needs local Arabic creative variant.
Olaya | Delivery relaunch | Yes | No | No | No | In progress | Delivery partner photography delayed.

## Dashboard
Franchise Dashboard
Review which regions are rollout-ready and where compliance is slipping.
Rollout summary | Value
Store count | 5
Average compliance | 73.8%
Stores ready or live | 3
Blocked or in-progress rollouts | 1
Region | Average compliance
Dubai | 87%
Abu Dhabi | 74%
Sharjah | 58%
Doha | 81%
Riyadh | 69%